## Architecture
CAT411 FRAMEWORK ARCHITECTURE
MODULE DEPENDENCY (5 LAYERS)
MODULE REFERENCE TABLE
Layer | Module | Role | Key API | Upstream | Downstream
L0 | hazus_params | Fragility parameters (14 HWB classes) | HAZUS_BRIDGE_FRAGILITY | — | bridge_classes, fragility, loss
L0 | config | YAML config loader | load_config(), AnalysisConfig | — | main
L1 | hazard | GMPE + ground motion fields | boore_atkinson_2008_sa10(), generate_ground_motion_fields() | — | engine, exposure
L1 | bridge_classes | NBI -> HWB classification | classify_bridge(), get_bridge_params() | hazus_params | data_loader
L1 | interpolation | Spatial interpolation (5 methods) | interpolate_im() | — | main
L2 | fragility | Fragility curves + skew modification | damage_state_probabilities(), apply_skew_modification() | hazus_params | loss, plotting, northridge_case
L2 | exposure | Portfolio + replacement cost | create_portfolio_from_nbi(), portfolio_to_sites() | hazard | engine
L2 | data_loader | Parse ShakeMap / NBI / stations | parse_shakemap_grid(), parse_nbi(), load_all() | bridge_classes | main
L3 | loss | Loss, EP curve, AAL | compute_portfolio_loss(), compute_ep_curve(), compute_aal() | fragility | engine
L3 | engine | Deterministic + probabilistic runner | run_deterministic(), run_probabilistic() | hazard, exposure, loss | main
L4 | plotting | 14+ visualizations | plot_analysis_summary(), plot_bridge_damage_map() | fragility | main
L4 | northridge_case | 1994 Northridge validation data | compare_predicted_vs_observed() | fragility | main
L4 | hazard_download | USGS data downloader | download_all_hazard_data() | — | main
Entry | main.py | CLI entry point (9 analysis modes) | run_data_analysis(), run_full_analysis() | ALL | (user)

## Module_Tasks
ID | Module | Task | P | Assignee | Status | Blocked By | Week | Notes
T01 | hazard | Review Hazus params for bridge types (Table 7.9 fragility) | P0 | Kubilay, Michel | IN_PROGRESS |  | W1 | Get Sa(1.0s) at 4,853 bridge sites
T02 | data_loader | NBI data quality check (missing values, coords, classification) | P0 | Sirisha | IN_PROGRESS |  | W1 | Confirm bridge data is clean
T03 | hazus_params | Spot-check median & beta values against HAZUS manual | P0 | Sirisha | IN_PROGRESS |  | W1 | Table 7.9 verification
T04 | ALL | Code + GitHub collaboration setup; leave blanks per module | P0 | Wenyu, Anik | IN_PROGRESS |  | W1 | Ongoing
T05 | ALL | Biweekly presentation slides | P0 | Kubilay, Michel | TODO |  | W1 | Summarize all work
T06 | data_loader | Verify %g -> g conversion consistency | P0 | Wenyu | DONE |  | W1 | Confirmed: parse_shakemap divides by 100
T07 | fragility | Fragility verification (monotonicity / bounds / sum) | P0 | Wenyu | DONE |  | W1 | Passed --fragility-only
T08 | hazard | Stabilize im_source decision flow (shakemap first) | P0 |  | TODO |  | W1 | main.py _compute_bridge_damage
T09 | interpolation | Benchmark interpolation methods (nearest vs IDW) | P0 |  | TODO | T08 | W1 | Compare on Northridge ShakeMap
T10 | ALL | Integration test: run_data_analysis end-to-end | P0 | Wenyu | TODO | T02,T08 | W1 | M1 acceptance gate
T11 | plotting | Plot fragility curves for all 14 HWB classes | P0 |  | TODO | T03 | W2 | Visual check: S-shaped, ordered
T12 | bridge_classes | Bridge classification check (NBI -> HWB mapping logic) | P0 |  | TODO | T02 | W2 | Correct class assignment
T13 | engine | Run full pipeline (hazard -> fragility -> loss) E2E | P0 |  | TODO | T10 | W2 | First results for all 4,853 bridges
T14 | loss | Validate expected_loss & loss_ratio reasonableness | P0 |  | TODO | T13 | W2 | Define acceptable range
T15 | loss | Verify count_by_ds sums to bridge count | P0 |  | TODO | T14 | W2
T16 | engine | Deterministic fixed-seed regression test | P0 |  | TODO | T14 | W2 | Drift threshold TBD
T17 | hazard | Collect multi-period GMPE coefficients (PGA, SA0.3, SA3.0) | P1 |  | TODO |  | W2 | Boore & Atkinson 2008 Tables
T18 | hazard | Obtain Vs30 grid for study region | P1 |  | TODO |  | W2 | USGS / Wills et al.
T19 | fragility | E2E test of fragility_overrides from config.yaml | P1 |  | TODO |  | W2 | Mechanism exists, untested
T20 | ALL | Unit tests: hazard / fragility / loss core functions | P1 |  | TODO |  | W2 | pytest structure TBD
T21 | northridge | Compare model output vs actual Northridge damage records | P0 |  | TODO | T13 | W3 | Match 170 real cases?
T22 | engine | Design functionality module (serviceability + recovery) | P1 |  | TODO | T13 | W3 | Can bridge carry traffic? Repair time?
T23 | config | Calibration factor sensitivity test (ON/OFF comparison) | P1 |  | TODO | T21 | W3
T24 | hazard | Implement GMPE path (currently NotImplementedError) | P1 |  | TODO | T17,T18 | W3 | Needs multi-period + Vs30
T25 | loss | Update damage ratio table (HAZUS MR4 -> MR5) | P1 |  | TODO |  | W3 | Compare versions
T26 | exposure | Define skew angle data source + replacement cost update | P1 |  | TODO |  | W3
T27 | plotting | Freeze dashboard indicator set | P2 |  | TODO |  | W3 | plot_analysis_summary metrics
T28 | report | Write results section (figures, tables, analysis) | P0 | ALL | TODO | T21 | W4 | Each person writes their module
T29 | report | Integrate all sections + final review | P0 | ALL | TODO | T28 | W4 | Complete draft of full report
T30 | plotting | Report templates (technical + management) | P2 |  | TODO | T27 | W4

## Data_Flow
DATA FLOW OVERVIEW
+-----------+ grid.xml +-----------+ Sa(g) array +-----------+ {DS: prob} +-----------+ E[L], AAL +-----------+ ¦ DATA ¦ -------------> ¦ HAZARD ¦ -------------> ¦ FRAGILITY ¦ -------------> ¦ LOSS ¦ ------------> ¦ OUTPUT ¦ ¦ LOADER ¦ NBI .txt ¦ MODULE ¦ per bridge ¦ MODULE ¦ per bridge ¦ MODULE ¦ EP curve ¦ MODULE ¦ +-----------+ -------------> +-----------+ +-----------+ +-----------+ +-----------+ ¦ ¦ ¦ ¦ ¦ parse_shakemap_grid() interpolate_im() damage_state_probs() compute_portfolio_loss() plot_*(), CSV parse_nbi() boore_atkinson_2008() apply_skew_mod() compute_ep_curve() dashboard classify_nbi_to_hazus() compute_aal() KEY DATA OBJECTS: ----------------- ShakeMap grid : DataFrame [lat, lon, pga, sa03, sa10, sa30] (units: g) NBI bridges : DataFrame [structure_number, lat, lon, hwb_class, material, deck_area, ...] BridgeExposure : dataclass [bridge_id, lat, lon, hwb_class, replacement_cost, vs30, skew_angle] SiteParams : dataclass [lat, lon, vs30] BridgeLossResult : [bridge_id, sa, damage_probs, expected_loss, loss_ratio] PortfolioLossResult : [total_loss, loss_ratio, loss_by_class, count_by_ds, AAL]
MODULE-TO-MODULE DATA MATRIX
FROM \ TO | hazus_params | bridge_classes | hazard | exposure | data_loader | fragility | interpolation | loss | engine | plotting | main
hazus_params | — | HAZUS_BRIDGE_FRAGILITY dict |  |  |  | HAZUS_BRIDGE_FRAGILITY, DAMAGE_STATE_ORDER |  | DAMAGE_STATE_ORDER |  | HAZUS_BRIDGE_FRAGILITY
bridge_classes |  | — |  |  | classify_bridge() -> HWB class string
hazard |  |  | — | SiteParams type import |  |  |  |  | EarthquakeScenario, Sa(g) arrays (n_sites x n_real)
exposure |  |  |  | — |  |  |  |  | list[BridgeExposure], list[SiteParams]
data_loader |  |  |  |  | — | [5 empty] | DataFrames: shakemap grid, NBI, stations
fragility | [5 empty] | — |  | damage_state_probabilities() -> {DS: float} |  | compute_all_curves() -> {DS: np.ndarray}
interpolation | [6 empty] | — |  |  |  | np.ndarray: IM values at bridge sites
loss | [7 empty] | — | PortfolioLossResult, EP curve dict, AAL float
engine | [8 empty] | — |  | DeterministicResult / ProbabilisticResult
plotting | [9 empty] | — | PNG file paths (str)
main | [10 empty] | —

## Literature
ID | Topic | Reference | Status | Assigned To | Module
L01 | GMPE | Boore & Atkinson (2008) — multi-period coefficients | PARTIAL |  | hazard
L02 | GMPE | Campbell & Bozorgnia (2008) — alternative NGA GMPE | TODO |  | hazard
L03 | Vs30 | Wills et al. (2015) / USGS Vs30 grid | TODO |  | hazard
L04 | Fragility | HAZUS-MH MR4/MR5 Technical Manual Ch.7 | IN_USE |  | hazus_params
L05 | Fragility | Shinozuka et al. (2000) — empirical bridge fragility | TODO |  | fragility
L06 | Damage Ratio | HAZUS Table 7.9 + Werner (2006) REDARS | PARTIAL |  | loss
L07 | Cost | RSMeans Heavy Construction Cost Data 2024 | TODO |  | exposure
L08 | Correlation | Jayaram & Baker (2009) — spatial correlation model | DONE |  | hazard
L09 | Validation | Basoz & Kiremidjian (1998) — Northridge bridge damage | PARTIAL |  | northridge_case
L10 | Classification | NBI Coding Guide (FHWA) | IN_USE |  | bridge_classes
L11 | Skew | HAZUS Technical Manual S7.2.4 — skew factor | PARTIAL |  | fragility
L12 | Hazard Map | USGS NSHM 2023 — probabilistic hazard curves | TODO |  | hazard_download
L13 | CAT Theory | Grossi & Kunreuther (2005) Catastrophe Modeling | TODO |  | engine
L14 | Fragility-TW | NCREE Bridge Fragility Reports (Taiwan) | TODO |  | fragility

## Timeline
MILESTONES & TIMELINE
TEAM: Wenyu (lead/code) ¦ Kubilay & Michel (hazard/params) ¦ Sirisha (data QA) ¦ Anik (code) Phase 1: HAZARD Phase 2: VULNERABILITY Phase 3: VALIDATION Phase 4: REPORT (data + params) (fragility + loss E2E) (Northridge + calibrate) (write + integrate) ------------------ ---------------------- ----------------------- ------------------- Review Hazus params Plot 14 HWB curves Model vs observed damage Results section NBI data quality HWB mapping check Functionality module Integrate + review Code/Git setup Run full pipeline E2E Sensitivity tests Final draft ¦--- W1: 2/19-2/25 ---¦--- W2: 2/26-3/4 ---¦--- W3: 3/5-3/11 ---¦--- W4: 3/12-3/18 ---¦ ¦ Phase 1: Hazard ¦ Phase 2: Vuln. ¦ Phase 3: Valid. ¦ Phase 4: Report ¦ ¦ << WE ARE HERE >> ¦ ¦ ¦ ¦
ID | Task | P | W1 2/19-2/25 | W2 2/26-3/4 | W3 3/5-3/11 | W4 3/12-3/18
T01 | MI Estimation(Kubilay, Michel) | P0 | ACTIVE
T02 | NBI data quality check (Sirisha) | P0 | ACTIVE
T03 | Spot-check median & beta (Sirisha) | P0 | ACTIVE
T04 | Code + GitHub collab (Wenyu, Anik) | P0 | ACTIVE | ACTIVE | ACTIVE | ACTIVE
T05 | Biweekly presentation (Kubilay, Michel) | P0 | ACTIVE
T06 | im_source stabilization | P0 | ACTIVE
T07 | Integration test E2E (Wenyu) | P0 | ACTIVE | DONE
T08 | Plot fragility curves (14 HWB) | P0 |  | ACTIVE
T09 | HWB classification check | P0 |  | ACTIVE
T10 | Run full pipeline E2E (4,853 bridges) | P0 |  | ACTIVE
T11 | Loss reasonableness check | P0 |  | ACTIVE
T12 | Collect GMPE coefficients | P1 |  | ACTIVE
T13 | Unit tests | P1 |  | ACTIVE | ACTIVE
T14 | Northridge: predicted vs observed | P0 |  |  | ACTIVE
T15 | Functionality module (serviceability) | P1 |  |  | ACTIVE
T16 | Calibration sensitivity test | P1 |  |  | ACTIVE
T17 | GMPE path implementation | P1 |  |  | ACTIVE
T18 | Write results section (ALL) | P0 |  |  |  | ACTIVE
T19 | Integrate sections + final review (ALL) | P0 |  |  |  | ACTIVE
Legend: | PLANNED | ACTIVE | DONE | BLOCKED

## Glossary
Term | Full Name | Definition
CAT | Catastrophe Model | Computational framework to estimate losses from natural disasters
GMPE | Ground Motion Prediction Equation | Empirical equation: IM = f(Mw, distance, Vs30, fault type)
IM | Intensity Measure | Quantitative ground shaking metric (PGA, SA at various periods)
PGA | Peak Ground Acceleration | Maximum ground surface acceleration, in units of g
SA10 | Spectral Acceleration at 1.0s | Default IM for HAZUS bridge fragility; primary IM in this framework
Vs30 | Shear-wave velocity (top 30m) | Site amplification proxy, units m/s (e.g., 760 = rock, 360 = stiff soil)
NBI | National Bridge Inventory | FHWA database of all US bridges with structural attributes
HWB | HAZUS Bridge Class | Classification HWB1-HWB28 based on material, span type, design era
DS | Damage State | Discrete levels: none / slight / moderate / extensive / complete
Fragility | Fragility Curve | P(DS >= ds ¦ IM) modeled as lognormal CDF with median & beta
EP | Exceedance Probability | Annual probability that loss exceeds a given $ threshold
AAL | Average Annual Loss | Expected annual loss = integral under EP curve
E[L] | Expected Loss | Probability-weighted loss across all damage states
LR | Loss Ratio | E[L] / replacement cost, dimensionless [0, 1]
Mw | Moment Magnitude | Standard earthquake magnitude scale used in GMPE
R_JB | Joyner-Boore Distance | Shortest distance from site to fault surface projection (km)
IDW | Inverse Distance Weighting | Spatial interpolation method, weight proportional to 1/d^p